## Summary
HINDUSTAN ENVIRO LIFE PROTECTION SERVICES LIMITED
CONSTRUCTION OF SECURED LANDFILL FACILITY AT VADGAM, KHAMBHAT
SUMMARY OF WORKS
SL NO | PARTICULARS | AMOUNT PHASE -01 UPTO WALL HEIGHT OF 5.40 M | AMOUNT PHASE -02 UPTO TOTAL HEIGHT OF 10.40 M | GRAND TOTAL
1 | Landfill | 0 | 0 | 0
2 | Liner Works | 0 | 0 | 0
| TOTAL AMOUNT | 0 | 0 | 0

## Abstract_Civil Works
NAME OF WORK - SECURED LANDFILL
HINDUSTAN ENVIRO LIFE PROTECTION SERVICES LIMITED, VADGAM, KHAMBHAT
BILL OF QUANTITY FOR SECURED LANDFILL WORKS
SL NO | BRIEF DESCRIPTION OF ITEM | UNIT | Qty Phase-1 | Qty Phase-2 | Qty Total | Rate | Amount Phase-1 | Amount Phase-2 | Amount Total
1 | Earth Work at the base of the phase
Mass Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead. See item No.1 of Item wise specifications
a) | Soft Soil | Cu.M. | 15930 | 0 | 15930 | 0 | 0 | 0 | 0
b) | Providing and laying 300mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete. | Cu.M. | 9731 | 0 | 9731 | 0 | 0 | 0 | 0
| Sub Total of Item 1 | [5 empty] | 0 | 0 | 0
2 | Construction of Earthen Bund on the Periphery of the phase at the back of RCC retaining wall:
| The item includes filling foundation and plinth with murrum or selected soil brought from outside of the site to construct earthen bunds on the periphery of the phase in layers not exceeding 23 cm. in depth and in such a way to maintain the prescribed side slope as shown. The item includes Excavation from borrow pits, transporting upto 25 km lead, filling, leveling, grading, dressing, watering and compaction of the earth from the excavation point to make earthen bunds in the prescribed side slopes. See item No.2 of Item wise specifications | Cu.M. | 19641 | 43954 | 63595 | 0 | 0 | 0 | 0
| Sub Total of Item 2 | [5 empty] | 0 | 0 | 0
3 | Construction of Retaining Wall in RCC M25 at the EGL of 10.364 m height and supported by RCC counterfortes:
The item includes construction of RCC M25 retaining wall of 300 mm thickness and 10.364 m total height at the existing ground level to increase the capacity of the phase. The wall shall be supported by RCC counterfortes and soil filling shall be done at the back of the wall for further support. The design and details are shown in the drawings. See item No.3 of Item wise specifications
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead. At the base of RCC wall. | Cu.M. | 12632 | 0 | 12632 | 0 | 0 | 0 | 0
b | Providing and laying 300mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete. | Cu.M. | 2238 | 0 | 2238 | 0 | 0 | 0 | 0
c | Providing and laying 150 mm thk. plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement. | Cu.M. | 1119 | 0 | 1119 | 0 | 0 | 0 | 0
d (i) | Providing and laying controlled cement concrete M-25 on the PCC laid above and curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing in Foundations, footings, base of columns and mass concrete. | Cu.M. | 5414 | 0 | 5414 | 0 | 0 | 0 | 0
d (ii) | Providing and laying controlled cement concrete M-25 wall and counterfortes from top of foundation level up to top height of wall. | Cu.M. | 4102 | 1335 | 5437 | 0 | 0 | 0 | 0
e | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. | Kg | 843286 | 133496 | 976782 | 0 | 0 | 0 | 0
f | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete and vertical wall structure. | Sq.M. | 29125 | 8859 | 37984 | 0 | 0 | 0 | 0
g | Providing and Laying of flat ribbed PVC Water stopper in the 25 mm wide expansion joint provided in the retaining RCC wall of size 300 mm x 8 mm over the total height of the wall. The item includes procuring the product, preparation of application system and fixing the product all inclusive. | Rmt | 81 | 75 | 156 | 0 | 0 | 0 | 0
h | Providing and fixing 25 mm thk. HD100 Polymer Expansion joint filler board in the expansion joint of the retaining wall and its counter fortes structure: 25 mm thk. HD100 Polymer based expansion joint filler board is a cross linked, pre moulded high performance joint filler board. It is readily compressible and ensures low load transfer. It is a closed cell with excellent chemical resistance, thermally stable upto 70oC, and very compressible as well as elastic with almost more than 90% recoverable to its original state and rot proof and bacteria resistant. The item includes procuring the product, preparation of application system and fixing the product all inclusive. | Sq.m. | 478 | 442 | 920 | 0 | 0 | 0 | 0
| Sub Total of Item 3 | [5 empty] | 0 | 0 | 0
4 | Amended Clay Liner in the Bottom - 2 Layers of 450 mm thickness
| The item includes P/L of amended clay liner using the available soil obtained from excavation of the phase as well as from the nearby borrow pits and mixing with good quality sodium bentonite in appropriate proportion with soil to achieve the desired permeability as specified in criteria of CPCB, on the bottom surface of the phase in two layers of 450 mm thickness as shown in the bottom liner section. The contractor shall mix the excavated soil and bentonite to fill the bottom liner in 450 mm thickness and compacted thorughly. See Item No.4 of Item wise specifications. | Cu.M. | 31374 | 0 | 31374 | 0 | 0 | 0 | 0
| Sub Total of Item 4 | [5 empty] | 0 | 0 | 0
5 | Drainage Layer at the Bottom of phase - 2 layers of 300 mm thickness
The item includes providing and laying of 300 mm drainage layer - primary and secondary layers comprising of 100mm thick 12-25 mm round gravels/Coarse Aggregate + 100 mm thick 3-12mm round gravels/Coarse Aggregate (Grit) + 100 mm thk. Coarse sand as shown in drawing. The item includes providing, laying, leveling, compaction etc. complete. See Item No.5 of Item wise specifications.
a | 100 mm thk. 12 -25 mm round gravels/coarse aggregate | Cu.M. | 6972 | 0 | 6972 | 0 | 0 | 0 | 0
b | 100 mm thk. 3 -12 mm round gravels/coarse aggregate | Cu.M. | 6972 | 0 | 6972 | 0 | 0 | 0 | 0
c | 100 mm thk. Coarse sand | Cu.M. | 6972 | 0 | 6972 | 0 | 0 | 0 | 0
| Sub Total of Item 5 | [5 empty] | 0 | 0 | 0
6 | Top Service Road of the Phase
Providing and laying of 4.00 M Wide (3.75 M Clear) CC road on the top periphery of the phase. The item includes excavation, 230 mm thk. Rubble Soling, 100 mm thk. PCC (1:4:8) and 100 mm thk. RCC M20 construction on the road. Total road area 3236 Sq.m. See Item No.6 of Item wise specifications.
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead. | Cu.M. | 0 | 330 | 330 | 0 | 0 | 0 | 0
b | Providing and laying 230mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete. | Cu.M. | 0 | 759 | 759 | 0 | 0 | 0 | 0
c | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement. | Cu.M. | 0 | 330 | 330 | 0 | 0 | 0 | 0
d | Providing and laying controlled cement concrete M-20 on the PCC laid above and curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing. | Cu.M. | 0 | 309 | 309 | 0 | 0 | 0 | 0
e | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. | Kg | 0 | 13922 | 13922 | 0 | 0 | 0 | 0
f | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete. | Sq.M. | 0 | 332 | 332 | 0 | 0 | 0 | 0
| Sub Total of Item 6 | [5 empty] | 0 | 0 | 0
7 | Kerb Wall on the Outer Edge of the Top Service Road - 300 mm high and 250 mm thk. - 830 m long
Construction of Kerb Wall on the outer edge of the 4.0 M Wide (3.75 M clear wide) Top service road on the top periphery of the phase. The item includes 250 mm thk. and 300 mm high RCC M20 construction on the road. See Item No.7 of Item wise specifications.
a | Providing and laying controlled cement concrete M-20 on the PCC laid above and curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing in Foundations, footings, base of columns and mass concrete. | Cu.M. | 0 | 62 | 62 | 0 | 0 | 0 | 0
b | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. | Kg | 0 | 4980 | 4980 | 0 | 0 | 0 | 0
c | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete. | Sq.M. | 0 | 498 | 498 | 0 | 0 | 0 | 0
| Sub Total of Item 7 | [5 empty] | 0 | 0 | 0
8 | Outer Side Slope Construction
Following works are to be carried out on the outer side slope of total length 12.90 Avg. m. The item includes protection of Outer side slope by P/L of 230 mm thk. Rubble Soling, 100 mm thk. PCC (1:4:8) and 100 mm thk. RCC M20 on the outer side slope. Total Area of outer side slope is 10965 Sq.m. See Item No.8 of Item wise specifications.
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead. | Cu.M. | 0 | 1664 | 1664 | 0 | 0 | 0 | 0
b | Providing and laying 230mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete. | Cu.M. | 0 | 2551 | 2551 | 0 | 0 | 0 | 0
c | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement. | Cu.M. | 0 | 1097 | 1097 | 0 | 0 | 0 | 0
d | Providing and laying controlled cement concrete M-20 on the PCC laid above and curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing in Foundations, footings, base of columns and mass concrete. | Cu.M. | 0 | 1088 | 1088 | 0 | 0 | 0 | 0
e | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. | Kg | 0 | 48960 | 48960 | 0 | 0 | 0 | 0
f | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete. | Sq.M. | 0 | 732 | 732 | 0 | 0 | 0 | 0
| Sub Total of Item 8 | [5 empty] | 0 | 0 | 0
9 | Storm Water Drain - 1020 m long, 0.50 m wide and 0.40 m deep [ 912 m around Landfill adjacent to toewall & 108 m other area without toewall]
The item includes construction of Storm Water Drain in RCC on the bottom outer edge of the outer side slope on the G/L. The item includes excavation, Rubble Soling, PCC and RCC M20. See Item No. 9 of Item wise specifications.
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead. | Cu.M. | 499 | 0 | 499 | 0 | 0 | 0 | 0
b | Providing and laying 230mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete. | Cu.M. | 220 | 0 | 220 | 0 | 0 | 0 | 0
c | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement. | Cu.M. | 82 | 0 | 82 | 0 | 0 | 0 | 0
d | Providing and laying controlled cement concrete M-20 on the PCC laid above and curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing in Foundations, footings, base of columns and mass concrete. | Cu.M. | 226 | 0 | 226 | 0 | 0 | 0 | 0
e | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. | Kg | 19228 | 0 | 19228 | 0 | 0 | 0 | 0
f | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete. | Sq.M. | 2091 | 0 | 2091 | 0 | 0 | 0 | 0
| Sub Total of Item 9 | [5 empty] | 0 | 0 | 0
10 | Toe Wall in Brick Masonary on outer side slope outer edge - 912 m length in landfill periphery
The item includes construction of Toe Wall in Brick Masonary on the bottom outer edge of the outer side slope on the G/L. The item includes excavation, rubble soling, PCC, B/M and Plaster. See Item No. 10 of Item wise specifications.
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead. | Cu.M. | 1585 | 0 | 1585 | 0 | 0 | 0 | 0
b | Providing and laying 230mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete. | Cu.M. | 220 | 0 | 220 | 0 | 0 | 0 | 0
c | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement. | Cu.M. | 68 | 0 | 68 | 0 | 0 | 0 | 0
d | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete. | Sq.M. | 183 | 0 | 183 | 0 | 0 | 0 | 0
e | Providing and laying the brick masonary of well burnt bricks of approved quality and manufacturer in cement mortar 1:6 prop. using screened coarse sand upto prescribed height of the wall. | Cu.m. | 240 | 0 | 240 | 0 | 0 | 0 | 0
f | Providing and applying 20 mm thick smooth plaster in cement mortar 1:4 prop., using screened coarse sand of approved quality on walls and RCC work as required incl. racking of joints of masonary and roughening of concrete surface (i.e. hacking) to receive plaster, with the use of approved water proofing admixture, with scaffolding to any height, finishing smooth with cement slurry mixing, applying, watering, curing with all labour and materials. | Sq.m. | 3926 | 0 | 3926 | 0 | 0 | 0 | 0
| Sub Total of Item 10 | [5 empty] | 0 | 0 | 0
11 | Leachate Well in RCC M25 - 4 Nos. - 6.0 m x 2.0 m x 2.665 m (H)
The leachate wells have to be constructed in RCC M250 grade concrete of size 6.0 m x 2.0 m x 2.665 m (H) with 200 mm thickness wall as shown in the drawing. The well shall be kept partly covered from the top. See Item No. 11 of Item wise specifications.
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead. | Cu.M. | 329 | 0 | 329 | 0 | 0 | 0 | 0
b | P/L of Rubble Soling in the Raft of the Tank | cu.m. | 37 | 0 | 37 | 0 | 0 | 0 | 0
c | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement. | Cu.M. | 14 | 0 | 14 | 0 | 0 | 0 | 0
d | Providing and laying controlled cement concrete M-25 in the raft and walls and slab of the wells and includes curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing. | Cu.M. | 63 | 0 | 63 | 0 | 0 | 0 | 0
e | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. | kg | 5626 | 0 | 5626 | 0 | 0 | 0 | 0
f | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete. | Sq.M. | 468 | 0 | 468 | 0 | 0 | 0 | 0
| Sub Total of Item 11 | [5 empty] | 0 | 0 | 0
12 | Leachate Collection system - Leachate pipes - 160 mm outer dia lateral pipes - 1768 m Length and 225 mm oter dia main header pipes - 332 m Length laid in RCC leachate Collection trench placed at the bottom of the phase in the Primary Leachate Collection layer
The item includes providing and laying of 160 mm outer diameter size HDPE pipes of 10 Kg/cm2 pressure grade and ISI make as per IS – 4984 with material grade PE – 80 and material density of 946.40 Kg/cm2 and having holes of 10 mm @ center to center 200 mm distance in the upper half section of the pipes, through out the length of the pipes as shown in the diagram attached. The pipes are to be laid horizontally in the primary drainage layer at the bottom of the phase as shown in the layout plan of the landfill and are connected with the RCC leachate wells. The pipes connecting the leachate well are to be laid in such a way so as to make a slope of 1.0 % available to allow leachate to flow easily in to the Leachate well. The pipes are to be laid in a RCC leachate collection trench. The Leachate wells are to be connected to a 225 mm outer diameter main header. The leachate wells shall have a leachate lifting system with sludge pumps provided at the G/L and delivery pipe brought to the G/L at the approach ramps and provided with valves for discharging leachate to the leachate tank. See Item No. 12 of Item wise specifications.
a | Providing and Laying of 160 mm diameter HDPE pipes of 10 Kg/CM2 grade and ISI make with perforations for leachate collection. | R.mt. | 1768 | 0 | 1768 | 0 | 0 | 0 | 0
b | Providing and Laying of 225 mm diameter HDPE pipes of 10 Kg/CM2 grade and ISI make without perforations for leachate collection - whole main header pipe. | R.mt. | 332 | 0 | 332 | 0 | 0 | 0 | 0
c | Providing and Laying of RCC Leachate Collection Trench to fix pipes at specified locations – 1768 m for 160mm Perforated HDPE pipes and 332 m for 225 mm main Header Pipe - Total 2100 m length:
c.1 | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead. | Cu.M. | 813 | 0 | 813 | 0 | 0 | 0 | 0
c.2 | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement. | Cu.M. | 378 | 0 | 378 | 0 | 0 | 0 | 0
c.3 | Providing and laying controlled cement concrete M-20 in the raft and walls of the wells and includes curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing. | Cu.m. | 294 | 0 | 294 | 0 | 0 | 0 | 0
c.4 | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. | Kg | 17640 | 0 | 17640 | 0 | 0 | 0 | 0
d | Providing and Laying of Sludge pumps with complete electrical system including high efficiency motor, operating at a discharge head of 30 m minimum and delivering the leachate at the rate of 50 Cum/Hr. - NON SOR ITEM | No. | 4 | 0 | 4 | 0 | 0 | 0 | 0
| Sub Total of Item 12 | [5 empty] | 0 | 0 | 0
13 | Construction of Outer Side Entrance Ramp up to Top Road for 5.4 m height wall construction in Phase -1
The item includes construction of Outer Entrance Ramp for Truck movement into and out of the phase. Total Ramp Length is 76 Rmt and 7.0 m wide, with top area of 548 Sq.m. And Side Slope area of 538 Sq.m.to be constructed by filling of soil and followed by rubble stone filling and kerb wall on both sides in brick masonary. See Item No. 13 of Item wise specifications.
a | The item includes filling foundation and plinth with murrum or selected soil brought from outside of the site to construct outer ramp for truck into & out to in layers not exceeding 23 cm. in depth and in such a way to maintain the prescribed side slope as shown. The item includes Excavation from borrow pits, transporting upto 25 km lead, filling, leveling, grading, dressing, watering and compaction of the earth from the excavation point to make outer ramp in the prescribed side slopes. | Cu.M. | 2464 | 0 | 2464 | 0 | 0 | 0 | 0
b | Providing and laying 300mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete. | Cu.M. | 321 | 0 | 321 | 0 | 0 | 0 | 0
c | Providing and laying plain cement concrete (1:4:8) at the outer edges of ramp and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement. | Cu.M. | 3 | 0 | 3 | 0 | 0 | 0 | 0
d | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete. | Sq.M. | 24 | 0 | 24 | 0 | 0 | 0 | 0
e | Providing and laying the brick masonary of well burnt bricks of approved quality and manufacturer in cement mortar 1:6 prop. using screened coarse sand in the kerb wall of size 345 mm (B) x 600 mm (H) | Cu.M. | 31 | 0 | 31 | 0 | 0 | 0 | 0
| Sub Total of Item 13 | [5 empty] | 0 | 0 | 0
14 | Construction of Outer Side Entrance Ramp up to Top Road for 8.70 m height wall construction in Phase -2 + Entrance area development
The item includes construction of Outer Entrance Ramp for Truck movement into and out of the phase. Total Ramp Length is 112.50 Rmt and 7.0 m wide, with top area of 785.50 Sq.m. And Side Slope area of 1335 Sq.m.to be constructed by filling of soil and followed by rubble stone filling, followed by PCC and RCC and kerb wall on both sides in RCC. It also includes construction of entrance area development in RCC. Additional Entrance Area to be developed is 1045 Sq.m. as shown in the layout drawing. See Item No. 14 of Item wise specifications.
a | The item includes filling foundation and plinth with murrum or selected soil brought from outside of the site to construct outer ramp for truck into & out to in layers not exceeding 23 cm. in depth and in such a way to maintain the prescribed side slope as shown. The item includes Excavation from borrow pits, transporting upto 25 km lead, filling, leveling, grading, dressing, watering and compaction of the earth from the excavation point to make outer ramp in the prescribed side slopes. | Cu.M. | 0 | 8680 | 8680 | 0 | 0 | 0 | 0
b | Providing and laying 230mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete. | Cu.M. | 0 | 729 | 729 | 0 | 0 | 0 | 0
c | Providing and laying plain cement concrete (1:4:8) at the outer edges of ramp and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement. | Cu.M. | 0 | 317 | 317 | 0 | 0 | 0 | 0
d | Providing and laying controlled cement concrete M-20 over the PCC area including all areas of the ramp and includes curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing. | Cu.m. | 0 | 1118 | 1118 | 0 | 0 | 0 | 0
e | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. | Kg | 0 | 78244 | 78244 | 0 | 0 | 0 | 0
f | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete. | Sq.M. | 0 | 362 | 362 | 0 | 0 | 0 | 0
| Sub Total of Item 14 | [5 empty] | 0 | 0 | 0
| GRAND TOTAL AMOUNT : | [5 empty] | 0 | 0 | 0

## Measurement_Civil Works_Total
NAME OF WORK - SECURED LANDFILL
HINDUSTAN ENVIRO LIFE PROTECTION SERVICES LIMITED, VADGAM, KHAMBHAT
BILL OF QUANTITY FOR SECURED LANDFILL - CIVIL WORKS
SL NO | BRIEF DESCRIPTION OF ITEM | UNIT | Nos | L | B | H | Qty
Earth Work at the base of the phase
1 | Mass Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead.
Soft Soil
| Inside Bottom Area | Cu.M. | 1 | 31860 |  | 0.5 | 15930
| Total Qty : | Cu.M. |  |  |  |  | 15930
2 | Providing and laying 300mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete.
| Inside Bottom Area | Cu.M. | 1 | 32435 |  | 0.3 | 9730.5
| Total Qty : | Cu.M. |  |  |  |  | 9730.5
Construction of Earthen Bund on the Periphery of the phase at the back of RCC retaining wall:
2 | The item includes filling foundation and plinth with murrum or selected soil brought from outside of the site to construct earthen bunds on the periphery of the phase in layers not exceeding 23 cm. in depth and in such a way to maintain the prescribed side slope as shown. The item includes Excavation from borrow pits, transporting upto 25 km lead, filling, leveling, grading, dressing, watering and compaction of the earth from the excavation point to make earthen bunds in the prescribed side slopes.
| Back Side of Landfill RCC Wall | Cu.M. | 1 | 850 | 8.415 | 8.7 | 62228.925
| Outer Footing Below NGL | Cu.M. | 1 | 813 | 5.6 | 0.3 | 1365.84
| Total Qty : | Cu.M. |  |  |  |  | 63594.765
Construction of Retaining Wall in RCC M25 at the EGL of 10.364 m height and supported by RCC counterfortes:
3 | The item includes construction of RCC M25 retaining wall of 300 mm thickness and 10.364 m total height at the existing ground level to increase the capacity of the phase. The wall shall be supported by RCC counterfortes and soil filling shall be done at the back of the wall for further support. The design and details are shown in the drawings.
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 100 mt. lead.
| At Base of Landfill RCC Wall | Cu.M. | 1 | 802 | 10.5 | 1.5 | 12631.5
| Total Qty : | Cu.M. |  |  |  |  | 12631.5
b | Providing and laying 300mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete.
| At Base of Landfill RCC Wall | Cu.M. | 1 | 802 | 9.3 | 0.3 | 2237.58
| Total Qty : | Cu.M. |  |  |  |  | 2237.58
c | Providing and laying 150 mm thk. plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| At Base of Landfill RCC Wall | Cu.M. | 1 | 802 | 9.3 | 0.15 | 1118.79
| Total Qty : | Cu.M. |  |  |  |  | 1118.79
d | Providing and laying controlled cement concrete M-25 on the PCC laid above and curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing in Foundations, footings, base of columns and mass concrete.
| Footing of RCC Wall | Cu.M. | 1 | 802 | 9 | 0.75 | 5413.5
| Total Qty : | Cu.M. |  |  |  |  | 5413.5
e | Wall and counterfortes from top of foundation level up to top height of wall.
| Vertical Wall | Cu.M. | 1 | 794 | 0.3 | 10.4 | 2477.28
| Counter Fortes on the back side of Wall | Cu.M. | 378 | 3 | 0.3 | 8.7 | 2959.74
| Total Qty : | Cu.M. |  |  |  |  | 5437.02
f | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. |  |  |  | Unit Wt. Kg per Cum
| Footing of RCC Wall | Kg | 1 | 5413.5 | 80 | 1 | 433080
| Verti Wall | Kg | 1 | 2477.28 | 100 | 1 | 247728
| Counter Fall back side Wall | Kg | 1 | 2959.74 | 100 | 1 | 295974
| Total Qty : | Kg |  |  |  |  | 976782
g | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete and vertical wall structure.
| For PCC at Base of Footing - Along Length | Sq.M. | 2 | 802 | 1 | 0.15 | 240.6
| For PCC at Base of Footing - Across Length | Sq.M. | 2 | 9 | 1 | 0.15 | 2.7
| For Footing of RCC Wall - Along Length | Sq.M. | 2 | 802 | 1 | 0.9 | 1443.6
| For Footing of RCC Wall - Across Length | Sq.M. | 2 | 9 | 1 | 0.9 | 16.2
| Verti Wall - Along Length | Sq.M. | 1 | 792 | 1 | 10.4 | 8236.8
| Verti Wall - Along Length | Sq.M. | 1 | 688 | 1 | 10.4 | 7155.2
| Verti Wall - Across Length | Sq.M. | 2 | 0.3 | 1 | 10.4 | 6.24
| Counter Forts Along Height & Width | Sq.M. | 756 | 3 | 1 | 8.7 | 19731.6
| Counter Forts Across Height & Width | Sq.M. | 378 | 0.3 | 1 | 10.15 | 1151.01
| Total Qty : | Sq.M. |  |  |  |  | 37983.95
h | Providing and Laying of flat ribbed PVC Water stopper in the 25 mm wide expansion joint provided in the retaining RCC wall of size 300 mm x 8 mm over the total height of the wall. | Rmt | 15 | 10.4 |  |  | 156
i | Providing and fixing 25 mm thk. HD100 Polymer Expansion joint filler board in the expansion joint of the retaining wall and its counter fortes structure: 25 mm thk. HD100 Polymer based expansion joint filler board is a cross linked, pre moulded high performance joint filler board. It is readily compressible and ensures low load transfer. It is a closed cell with excellent chemical resistance, thermally stable upto 70oC, and very compressible as well as elastic with almost more than 90% recoverable to its original state and rot proof and bacteria resistant. | Sq.m. | 15 | 1 | 5.9 | 10.4 | 920.4
Amended Clay Liner in the Bottom - 2 Layers of 450 mm thickness
4 | The item includes P/L of amended clay liner using the available soil obtained from excavation of the phase as well as from the nearby borrow pits and mixing with good quality sodium bentonite in appropriate proportion with soil to achieve the desired permeability as specified in criteria of CPCB, on the bottom surface of the phase in two layers of 450 mm thickness as shown in the bottom liner section. The contractor shall mix the excavated soil and bentonite to fill the bottom liner in 450 mm thickness and compacted thorughly. See Item No.4 of Item wise specifications.
| Inside Bottom Area - 1st layer | Cu.M. | 1 | 34860 |  | 0.45 | 15687
| Inside Bottom Area - 2nd layer | Cu.M. | 1 | 34860 |  | 0.45 | 15687
| Total Qty : | Cu.M. |  |  |  |  | 31374
Drainage Layer at the Bottom of phase - 2 layers of 300 mm thickness
5 | The item includes providing and laying of 300 mm drainage layer - primary and secondary layers comprising of 100mm thick 12-25 mm round gravels/Coarse Aggregate + 100 mm thick 3-12mm round gravels/Coarse Aggregate (Grit) + 100 mm thk. Coarse sand as shown in drawing. The item includes providing, laying, leveling, compaction etc. complete. See Item No.5 of Item wise specifications.
a | 100 mm thk. 12 -25 mm round gravels/coarse aggregate
| Inside Bottom Area - 1st layer | Cu.M. | 1 | 34860 |  | 0.1 | 3486
| Inside Bottom Area - 2nd layer | Cu.M. | 1 | 34860 |  | 0.1 | 3486
| Total Qty : | Cu.M. |  |  |  |  | 6972
b | 100 mm thk. 3 -12 mm round gravels/coarse aggregate
| Inside Bottom Area - 1st layer | Cu.M. | 1 | 34860 |  | 0.1 | 3486
| Inside Bottom Area - 2nd layer | Cu.M. | 1 | 34860 |  | 0.1 | 3486
| Total Qty : | Cu.M. |  |  |  |  | 6972
c | 100 mm thk. Coarse sand
| Inside Bottom Area - 1st layer | Cu.M. | 1 | 34860 |  | 0.1 | 3486
| Inside Bottom Area - 2nd layer | Cu.M. | 1 | 34860 |  | 0.1 | 3486
| Total Qty : | Cu.M. |  |  |  |  | 6972
Top Service Road of the Phase
6 | Providing and laying of 3.75 M Clear Wide CC road on the top periphery of the phase. The item includes excavation, 230 mm thk. Rubble Soling, 100 mm thk. PCC (1:4:8) and 100 mm thk. RCC M20 construction on the road. Total road area 3236 Sq.m.:
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead.
| For Top Road surface dressing | Cu.M. | 1 | 825 | 4 | 0.1 | 330
| Total Qty : | Cu.M. |  |  |  |  | 330
b | Providing and laying 230mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete.
| For Top Road rubble soling | Cu.M. | 1 | 825 | 4 | 0.23 | 759
| Total Qty : | Cu.M. |  |  |  |  | 759
c | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| For Top Road PCC | Cu.M. | 1 | 825 | 4 | 0.1 | 330
| Total Qty : | Cu.M. |  |  |  |  | 330
d | Providing and laying controlled cement concrete M-20 on the PCC laid above and curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing in Foundations, footings, base of columns and mass concrete.
| For Top Road RCC | Cu.M. | 1 | 825 | 3.75 | 0.1 | 309.375
| Total Qty : | Cu.M. |  |  |  |  | 309.375
e | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. |  |  |  | Unit Wt. Kg per Cum
| For Top Road RCC | Kg | 1 | 309.375 | 45 | 1 | 13921.875
| Total Qty : | Kg |  |  |  |  | 13921.875
f | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete.
| For PCC - Along Length | Sq.M. | 2 | 825 | 1 | 0.1 | 165
| For PCC - Across Length | Sq.M. | 2 | 4 | 1 | 0.1 | 0.8
| For RCC - Along Length | Sq.M. | 2 | 825 | 1 | 0.1 | 165
| For RCC - Across Length | Sq.M. | 2 | 3.75 | 1 | 0.1 | 0.75
| Total Qty : | Sq.M. |  |  |  |  | 331.55
Kerb Wall on the Outer Edge of the Top Service Road - 300 mm high and 250 mm thk. - 830 m long
7 | Construction of Kerb Wall on the outer edge of the 4.0 M Wide (3.75 M clear wide) Top service road on the top periphery of the phase. The item includes 250 mm thk. and 300 mm high RCC M20 construction on the road. See Item No.7 of Item wise specifications.
a | Providing and laying controlled cement concrete M-20 on the PCC laid above and curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing in Foundations, footings, base of columns and mass concrete.
| For Top Road RCC | Cu.M. | 1 | 830 | 0.25 | 0.3 | 62.25
| Total Qty : | Cu.M. |  |  |  |  | 62.25
b | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. |  |  |  | Unit Wt. Kg per Cum
| For Top Road RCC | Kg | 1 | 62.25 | 80 | 1 | 4980
| Total Qty : | Kg |  |  |  |  | 4980
c | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete.
| For RCC - Along Length | Sq.M. | 2 | 830 | 1 | 0.3 | 498
| For RCC - Across Length | Sq.M. | 2 | 1 | 0.25 | 0.3 | 0.15
| Total Qty : | Sq.M. |  |  |  |  | 498.15
Outer Side Slope Construction
8 | Following works are to be carried out on the outer side slope of total length 12.90 Avg. m. The item includes protection of Outer side slope by P/L of 230 mm thk. Rubble Soling, 100 mm thk. PCC (1:4:8) and 100 mm thk. RCC M20 on the outer side slope. Total Area of outer side slope is 10965 Sq.m.
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead.
| For Outer Side Slope surface dressing | Cu.M. | 1 | 850 | 13.05 | 0.15 | 1663.875
| Total Qty : | Cu.M. |  |  |  |  | 1663.875
b | Providing and laying 230mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete.
| For Outer Side Slope Rubble Soling | Cu.M. | 1 | 850 | 13.05 | 0.23 | 2551.275
| Total Qty : | Cu.M. |  |  |  |  | 2551.275
c | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| For Outer Side Slope PCC | Cu.M. | 1 | 850 | 12.9 | 0.1 | 1096.5
| Total Qty : | Cu.M. |  |  |  |  | 1096.5
d | Providing and laying controlled cement concrete M-20 on the PCC laid above and curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing in Foundations, footings, base of columns and mass concrete.
| For Outer Side Slope RCC | Cu.M. | 1 | 850 | 12.8 | 0.1 | 1088
| Total Qty : | Cu.M. |  |  |  |  | 1088
e | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. |  |  |  | Unit Wt. Kg per Cum
| For Outer Side Slope RCC | Kg | 1 | 1088 | 45 | 1 | 48960
| Total Qty : | Kg |  |  |  |  | 48960
f | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete.
| PCC - Along Length | Sq.M. | 285 | 12.9 | 0.1 | 1 | 367.65
| RCC - Along Length | Sq.M. | 285 | 12.8 | 0.1 | 1 | 364.8
| Total Qty : | Sq.M. |  |  |  |  | 732.45
Storm Water Drain - 1020 m long, 0.50 m wide and 0.40 m deep [ 912 m around Landfill adjacent to toewall & 108 m other area without toewall]
9 | The item includes construction of Storm Water Drain in RCC on the bottom outer edge of the outer side slope on the G/L. The item includes excavation, Rubble Soling, PCC and RCC M20.
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead.
| For Drain around Landfill Cell | Cu.M. | 1 | 912 | 0.515 | 0.855 | 401.5764
| For Drain other portion | Cu.M. | 1 | 108 | 1.05 | 0.86 | 97.524
| Total Qty : | Cu.M. |  |  |  |  | 499.1004
b | Providing and laying 230mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete.
| For Drain around Landfill Cell | Cu.M. | 1 | 912 | 0.925 | 0.23 | 194.028
| For Drain other portion | Cu.M. | 1 | 108 | 1.05 | 0.23 | 26.082
| Total Qty : | Cu.M. |  |  |  |  | 220.11
c | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| For Drain around Landfill Cell | Cu.M. | 1 | 912 | 0.775 | 0.1 | 70.68
| For Drain other portion | Cu.M. | 1 | 108 | 1.05 | 0.1 | 11.34
| Total Qty : | Cu.M. |  |  |  |  | 82.02
d | Providing and laying controlled cement concrete M-20 on the PCC laid above and curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing in Foundations, footings, base of columns and mass concrete.
| For Drain around Landfill Cell - Bottom | Cu.M. | 1 | 912 | 0.625 | 0.125 | 71.25
| For Drain of other portion - Bottom | Cu.M. | 1 | 108 | 0.75 | 0.125 | 10.125
| For Drain around Landfill Cell - Inner Wall | Cu.M. | 1 | 912 | 0.23 | 0.4 | 83.904
| For Drain of other portion - Inner Wall | Cu.M. | 1 | 108 | 0.23 | 0.4 | 9.936
| For All Drain Length - Outer Wall | Cu.M. | 1 | 1020 | 0.125 | 0.4 | 51
| Total Qty : | Cu.M. |  |  |  |  | 226.215
e | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. |  |  |  | Unit Wt. Kg per Cum
| For All Drain Length | Kg | 1 | 226.215 | 85 | 1 | 19228.275
| Total Qty : | Kg |  |  |  |  | 19228.275
f | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete.
| For All Drain Length - PCC | Sq.M. | 2 | 1020 | 1 | 0.1 | 204
| For All Drain Length - Inner Face | Sq.M. | 2 | 1020 | 1 | 0.4 | 816
| For All Drain Length - Outer Face | Sq.M. | 2 | 1020 | 1 | 0.525 | 1071
| Total Qty : | Sq.M. |  |  |  |  | 2091
Toe Wall in Brick Masonary on outer side slope outer edge - 912 m length in landfill periphery
10 | The item includes construction of Toe Wall in Brick Masonary on the bottom outer edge of the outer side slope on the G/L. The item includes excavation, rubble soling, PCC, B/M and Plaster.
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead.
| At the End of Outer Slope | Cu.M. | 1 | 912 | 1.05 | 1.655 | 1584.828
| Total Qty : | Cu.M. |  |  |  |  | 1584.828
b | Providing and laying 230mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete.
| At the Base of Toe Wall | Cu.M. | 1 | 912 | 1.05 | 0.23 | 220.248
| Total Qty : | Cu.M. |  |  |  |  | 220.248
c | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| At the Fdn of Toe Wall - PCC | Cu.M. | 1 | 912 | 0.75 | 0.1 | 68.4
| Total Qty : | Cu.M. |  |  |  |  | 68.4
d | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete.
| For Toe Wall - PCC - Along Length | Sq.M. | 2 | 912 | 1 | 0.1 | 182.4
| For Toe Wall - PCC - Across Length | Sq.M. | 2 | 1 | 0.75 | 0.1 | 0.15
| Total Qty : | Sq.M. |  |  |  |  | 182.55
e | Providing and laying the brick masonary of well burnt bricks of approved quality and manufacturer in cement mortar 1:6 prop. using screened coarse sand upto 3Meter Height including scaffolding.
| For Toe Wall - 450mm width | Cu.M. | 1 | 912 | 0.45 | 0.23 | 94.392
| For Toe Wall - 350mm width | Cu.M. | 1 | 912 | 0.35 | 0.24 | 76.608
| For Toe Wall - 230mm width | Cu.M. | 1 | 912 | 0.23 | 0.33 | 69.2208
| Total Qty : | Cu.M. |  |  |  |  | 240.2208
f | Providing and applying 20 mm thick smooth plaster in cement mortar 1:4 prop., using screened coarse sand of approved quality on brick walls and RCC work as required incl. racking of joints of masonary and roughening of concrete surface (i.e. hacking) to receive plaster, with the use of approved water proofing admixture, with scaffolding to any height, finishing smooth with cement slurry mixing, applying, watering, curing with all labour and materials.
| For Toe Wall - Both Sides - 230 mm width | Sq.M. | 2 | 912 | 1 | 0.33 | 601.92
| For Toe Wall - Both Sides - 350 mm width | Sq.M. | 2 | 912 | 1 | 0.24 | 437.76
| For Toe Wall - Both Sides - 450 mm width | Sq.M. | 2 | 912 | 1 | 0.23 | 419.52
| For RCC Drain - Outer Side | Sq.M. | 2 | 912 | 1 | 0.525 | 957.6
| For RCC Drain - Inside | Sq.M. | 2 | 912 | 1 | 0.4 | 729.6
| For RCC Drain - Top & Bottom of Drain | Sq.M. | 1 | 912 | 1 | 0.855 | 779.76
| Total Qty : | Sq.M. |  |  |  |  | 3926.16
Leachate Well in RCC M25 - 4 Nos. - 6.0 m x 2.0 m x 2.665 m (H)
11 | The leachate wells have to be constructed in RCC M250 grade concrete of size 6.0 m x 2.0 m x 2.665 m (H) with 200 mm thickness wall as shown in the drawing. The well shall be kept partly covered from the top.
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead.
| Leachate Tank Fdn - 4 Nos | Cu.M. | 4 | 7.9 | 3.9 | 2.67 | 329.0508
| Total Qty : | Cu.M. |  |  |  |  | 329.0508
b | P/L of Rubble Soling in the Raft of the Tank
| Leachate Tank Fdn Rubble Soling - 4 Nos | Cu.M. | 4 | 7.9 | 3.9 | 0.3 | 36.972
| Total Qty : | Cu.M. |  |  |  |  | 36.972
c | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| Leachate Tank Fdn PCC - 4 Nos | Cu.M. | 4 | 7.3 | 3.3 | 0.15 | 14.454
| Total Qty : | Cu.M. |  |  |  |  | 14.454
d | Providing and laying controlled cement concrete M-25 in the raft and walls and slab of the wells and includes curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing.
| Leachate Tank RCC Raft - 4 Nos | Cu.M. | 4 | 7 | 3 | 0.3 | 25.2
| Leachate Tank RCC Long Wall - 4 Nos | Cu.M. | 8 | 6 | 0.2 | 2.665 | 25.584
| Leachate Tank RCC Short Wall - 4 Nos | Cu.M. | 8 | 2 | 0.2 | 2.665 | 8.528
| Leachate Tank RCC Top Slab - 4 Nos | Cu.M. | 4 | 6 | 2 | 0.1 | 4.8
| Deduct : Slab Open Space - 4 Nos | Cu.M. | 4 | 2 | 2 | 0.1 | -1.6
| Total Qty : | Cu.M. |  |  |  |  | 62.512
e | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. |  |  |  | Unit Wt. Kg per Cum
| For All Drain Length | Kg | 1 | 62.512 | 90 | 1 | 5626.08
| Total Qty : | Kg |  |  |  |  | 5626.08
f | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete.
| For PCC - 4 Nos | Sq.M. | 8 | 7.3 | 1 | 0.15 | 8.76
| For PCC - 4 Nos | Sq.M. | 8 | 3.3 | 1 | 0.15 | 3.96
| For RCC Raft - 4 Nos | Sq.M. | 8 | 7 | 1 | 0.3 | 16.8
| For RCC Raft - 4 Nos | Sq.M. | 8 | 3 | 1 | 0.3 | 7.2
| For RCC Long Wall - Out Side - 4 Nos | Sq.M. | 8 | 6.4 | 1 | 2.665 | 136.448
| For RCC Long Wall - In Side - 4 Nos | Sq.M. | 8 | 6 | 1 | 2.565 | 123.12
| For RCC Short Wall - Out Side - 4 Nos | Sq.M. | 8 | 2.4 | 1 | 2.665 | 51.168
| For RCC Short Wall - In Side - 4 Nos | Sq.M. | 8 | 2 | 1 | 2.565 | 41.04
| For RCC Slab Bottom - 4 Nos | Sq.M. | 8 | 6 | 2 | 1 | 96
| Deduct : Open Space in RCC Slab Bottom - 4 Nos | Sq.M. | 4 | 2 | 2 | 1 | -16
| Total Qty : | Sq.M. |  |  |  |  | 468.496
Leachate Collection system - Leachate pipes - 160 mm outer dia lateral pipes - 1768 m Length and 225 mm oter dia main header pipes - 332 m Length laid in RCC leachate Collection trench placed at the bottom of the phase in the Primary Leachate Collection layer
12 | The item includes providing and laying of 160 mm outer diameter size HDPE pipes of 10 Kg/cm2 pressure grade and ISI make as per IS – 4984 with material grade PE – 80 and material density of 946.40 Kg/cm2 and having holes of 10 mm @ center to center 200 mm distance in the upper half section of the pipes, through out the length of the pipes as shown in the diagram attached. The pipes are to be laid horizontally in the primary drainage layer at the bottom of the phase as shown in the layout plan of the landfill and are connected with the RCC leachate wells. The pipes connecting the leachate well are to be laid in such a way so as to make a slope of 1.0 % available to allow leachate to flow easily in to the Leachate well. The pipes are to be laid in a RCC leachate collection trench. The Leachate wells are to be connected to a 225 mm outer diameter main header. The leachate wells shall have a leachate lifting system with sludge pumps provided at the G/L and delivery pipe brought to the G/L at the approach ramps and provided with valves for discharging leachate to the leachate tank. See Item No. 12 of Item wise specifications.
a | Providing and Laying of 160 mm diameter HDPE pipes of 10 Kg/CM2 grade and ISI make with perforations for leachate collection.
| Lateral Pipe | R.mt. | 1 | 1768 | 1 | 1 | 1768
| Total Qty : | R.mt. |  |  |  |  | 1768
b | Providing and Laying of 225 mm diameter HDPE pipes of 10 Kg/CM2 grade and ISI make without perforations for leachate collection - whole main header pipe.
| Header Pipe | R.mt. | 1 | 332 | 1 | 1 | 332
| Total Qty : | R.mt. |  |  |  |  | 332
c | Providing and Laying of RCC Leachate Collection Trench to fix pipes at specified locations – 1768 m for 160mm Perforated HDPE pipes and 332 m for 225 mm main Header Pipe - Total 2100 m length:
c.1 | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead.
| For Header & Lateral Pipe | Cu.M. | 1 | 2100 | 1.075 | 0.36 | 812.7
| Total Qty : | Cu.M. |  |  |  |  | 812.7
c.2 | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| For Header & Lateral Pipe | Cu.M. | 1 | 2100 | 1.8 | 0.1 | 378
| Total Qty : | Cu.M. |  |  |  |  | 378
c.3 | Providing and laying controlled cement concrete M-20 in the raft and walls of the wells and includes curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing.
| For Header & Lateral Pipe | Cu.M. | 1 | 2100 | 1.4 | 0.1 | 294
| Total Qty : | Cu.M. |  |  |  |  | 294
c.4 | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. |  |  |  | Unit Wt. Kg per Cum
| For Header & Lateral Pipe - RCC Bottom | Kg | 1 | 294 | 60 | 1 | 17640
| Total Qty : | Kg |  |  |  |  | 17640
d | Providing and Laying of Sludge pumps with complete electrical system including high efficiency motor, operating at a discharge head of 30 m minimum and delivering the leachate at the rate of 50 Cum/Hr. - NON SOR ITEM
| Sludge Pump - 4 Nos Tank | No. | 4 | 1 | 1 | 1 | 4
| Total Qty : | No. |  |  |  |  | 4
Construction of Outer Side Entrance Ramp up to Top Road for 5.4 m height wall construction in Phase -1
13 | The item includes construction of Outer Entrance Ramp for Truck movement into and out of the phase. Total Ramp Length is 76 Rmt and 7.0 m wide, with top area of 548 Sq.m. And Side Slope area of 538 Sq.m.to be constructed by filling of soil and followed by rubble stone filling and kerb wall on both sides in brick masonary.
a | The item includes filling foundation and plinth with murrum or selected soil brought from outside of the site to construct outer ramp for truck into & out to in layers not exceeding 20 cm. in depth and in such a way to maintain the prescribed side slope as shown. The item includes Excavation from borrow pits, transporting upto 25 km lead, filling, leveling, grading, dressing, watering and compaction of the earth from the excavation point to make outer ramp in the prescribed side slopes.
| Soil in Rectangular portion of 7 m width | Cu.M. | 1 | 76 | 7 | 2.529 | 1345.428
| Soil in Triangular portion of varying length | Cu.M. | 1 | 76 | 5.815 | 2.53 | 1118.1082
| Total Qty : | Cu.M. |  |  |  |  | 2463.5362
b | Providing and laying 300mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete.
| On top portion of 7 m width | Cu.M. | 1 | 76 | 7 | 0.3 | 159.6
| On side Slope portion | Cu.M. | 1 | 76 | 7.08 | 0.3 | 161.424
| Total Qty : | Cu.M. |  |  |  |  | 321.024
c | Providing and laying plain cement concrete (1:4:8) at the outer edges of ramp and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| At the outer edge of the ramp | Cu.M. | 1 | 76 | 0.445 | 0.1 | 3.382
| Total Qty : | Cu.M. |  |  |  |  | 3.382
d | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete.
| For PCC - Along Length | Sq.M. | 25 | 9.75 | 1 | 0.1 | 24.375
| For PCC - Across Length | Sq.M. | 2 | 1 | 0.345 | 0.1 | 0.069
| Total Qty : | Sq.M. |  |  |  |  | 24.444
e | Providing and laying the brick masonary of well burnt bricks of approved quality and manufacturer in cement mortar 1:6 prop. using screened coarse sand in the kerb wall of size 345 mm (B) x 600 mm (H)
| For Kerb Wall - 345 mm width | Cu.M. | 2 | 76 | 0.345 | 0.6 | 31.464
| Total Qty : | Cu.M. |  |  |  |  | 31.464
Construction of Outer Side Entrance Ramp up to Top Road for 8.70 m height wall construction in Phase -2 + Entrance area development
14 | The item includes construction of Outer Entrance Ramp for Truck movement into and out of the phase. Total Ramp Length is 112.50 Rmt and 7.0 m wide, with top area of 785.50 Sq.m. And Side Slope area of 1335 Sq.m.to be constructed by filling of soil and followed by rubble stone filling, followed by PCC and RCC and kerb wall on both sides in RCC. It also includes construction of entrance area development in RCC. Additional Entrance Area to be developed is 1045 Sq.m. as shown in the layout drawing. See Item No. 14 of Item wise specifications.
a | The item includes filling foundation and plinth with murrum or selected soil brought from outside of the site to construct outer ramp for truck into & out to in layers not exceeding 23 cm. in depth and in such a way to maintain the prescribed side slope as shown. The item includes Excavation from borrow pits, transporting upto 25 km lead, filling, leveling, grading, dressing, watering and compaction of the earth from the excavation point to make outer ramp in the prescribed side slopes.
| Soil in Rectangular portion of 7 m width | Cu.M. | 1 | 112.5 | 7 | 4.272 | 3364.2
| Soil in Triangular portion of varying length | Cu.M. | 1 | 112.5 | 8.891 | 4.27 | 4271.0141
| Soil in Entrance Area | Cu.M. | 1 | 149.28 | 7 | 1 | 1044.96
| Total Qty : | Cu.M. |  |  |  |  | 8680.1741
b | Providing and laying 230mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete.
| On top portion of 7 m width | Cu.M. | 1 | 112.5 | 7 | 0.23 | 181.125
| On side Slope portion | Cu.M. | 1 | 112.5 | 11.867 | 0.23 | 307.0586
| On Entrance Area | Cu.M. | 1 | 149.28 | 7 | 0.23 | 240.3408
| Total Qty : | Cu.M. |  |  |  |  | 728.5244
c | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| On top portion of 7 m width | Cu.M. | 1 | 112.5 | 7 | 0.1 | 78.75
| On side Slope portion | Cu.M. | 1 | 112.5 | 11.867 | 0.1 | 133.5038
| On Entrance Area | Cu.M. | 1 | 149.28 | 7 | 0.1 | 104.496
| Total Qty : | Cu.M. |  |  |  |  | 316.7498
d | Providing and laying controlled cement concrete M-20 over the PCC area including all areas of the ramp and includes curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing.
| On top portion of 7 m width | Cu.M. | 1 | 112.5 | 7 | 0.1 | 78.75
| On side Slope portion | Cu.M. | 1 | 112.5 | 11.867 | 0.1 | 133.5038
| In kerb wall on outer edge on both sides | Cu.M. | 1 | 112.5 | 11.867 | 0.6 | 801.0225
| On Entrance Area | Cu.M. | 1 | 149.28 | 7 | 0.1 | 104.496
| Total Qty : | Cu.M. |  |  |  |  | 1117.7723
e | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. |  |  |  | Unit Wt. Kg per Cum
| For Ramp - RCC | Kg | 1 | 1117.7723 | 70 | 1 | 78244.0575
| Total Qty : | Kg |  |  |  |  | 78244.0575
f | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete.
On top portion of ramp
| For PCC - Along Length | Sq.M. | 2 | 112.5 | 1 | 0.1 | 22.5
| For PCC - Across Length | Sq.M. | 2 | 7 | 1 | 0.1 | 1.4
| For RCC - Along Length | Sq.M. | 2 | 112.5 | 1 | 0.1 | 22.5
| For RCC - Across Length | Sq.M. | 2 | 7 | 1 | 0.1 | 1.4
| For Kerb wall Along length | Sq.M. | 2 | 112.5 | 1 | 0.6 | 135
On side slope portion of ramp
| For PCC | Sq.M. | 38 | 15.68 | 1 | 0.1 | 59.584
| For RCC | Sq.M. | 38 | 15.68 | 1 | 0.1 | 59.584
| On Entrance Area for PCC | Sq.M. | 2 | 149.28 | 1 | 0.1 | 29.856
| On Entrance Area for RCC | Sq.M. | 2 | 149.28 | 1 | 0.1 | 29.856
| Total Qty : | Sq.M. |  |  |  |  | 361.68

## Abstract_Liner Works
NAME OF WORK - SECURED LANDFILL
HINDUSTAN ENVIRO LIFE PROTECTION SERVICES LIMITED, VADGAM, KHAMBHAT
BILL OF QUANTITY FOR SECURED LANDFILL - LINER WORKS
SL NO | BRIEF DESCRIPTION OF ITEM | UNIT | Qty Phase-1 | Qty Phase-2 | Qty Total | Rate | Amount Phase-1 | Amount Phase-2 | Amount Total
1 | 1.5 mm HDPE Liner
| The item includes providing and laying of 1500 microns virgin quality HDPE liner. It shall be applied on the Geosynthetic Clay Liner and anchored below in the soil as shown in the section drawing. It shall be sealed and packed from both ends with the existing layers by employing combiwedge fusion process. The over lapping between two HDPE sheets shall be minimum 100 mm and the machine welding shall produce two sealing lines between one overlap for perfect sealing of the liner. The lining material shall be of highest quality high density polyethylene (HDPE) sheeting, manufactured in using virgin high density polyethylene resin entirely free of Plasticizers or other filler materials with all labours, tools, tackles, machineries and transportation. The material should comply all the physico chemical properties as specified i.e. Tear resistance, Puncture resistance, Tensile strength at yield and break, Carbon black content, density, etc. All the individual sheets shall be tested accordingly. The measurements shall be taken of the covered area only and no overlaps will be considered. Refer Item No. 1 for detailed specifications of Technical Specifications of liner works in the Technical Bid Document. - NON SOR ITEM - MARKET RATE | Sq.M. | 76056 | 6102 | 82158 | 0 | 0 | 0 | 0
2 | Providing and Laying of 500 gsm Geotextile Liner
| The item includes providing and laying of 500 gsm Geotextile liner. Refer Item No. 2 for detailed specifications of Technical Specifications of liner works in the Technical Bid Document. NON SOR ITEM - MARKET RATE | Sq.M. | 76056 | 6102 | 82158 | 0 | 0 | 0 | 0
3 | Providing and Laying of 150 GSM unprocessed non woven Geotextile Liner
| The item includes providing and laying of 150 gsm unprocessed non woven Geotextile liner laid and wrapped over the 160/225 mm HDPE perforated leachate collection pipe so as to allow leachate to flow to the leachate collection pipe and finally to the leachate collection well. This shall permit high flow of leachate into the leachate collection pipe and shall carry leachate to the leachate well. The liner shall be placed over the leachate collection pipe system as shown in the drawing. Refer Item No. 3 for detailed specifications of Technical Specifications of liner works in the Technical Bid Document. - NON SOR ITEM - MARKET RATE | Sq.M. | 1675 | 0 | 1675 | 0 | 0 | 0 | 0
4 | Supplying and applying HOT BITUMEN VG10 grade conforming to IS:73 @2.0 Kg/sq.m. on Concrete/Brick work surfaces etc.
| The item includes Supplying and applying one coat of HOT BITUMEN VG10 grade conforming to IS:73 @1.2 Kg/sq.m. & Supplying and applying Second coat of HOT BITUMEN VG10 grade conforming to IS:73 @0.8 Kg/sq.m. to be applied on the RCC retaining wall surface inside as well as on outside to prevent corrosion of RCC and Steel due to coastal area. This shall prevent any chemical attack on the concrete surface from the chemicals present in the hazardous wastes. The hot bitumen shall be applying over the retaining wall and on outer slopein hot conditions as shown in the drawing. Refer Item No. 4 for detailed specifications of Technical Specifications of liner works in the Technical Bid Document. - NON SOR ITEM - MARKET RATE | Sq.M. | 7681 | 18182 | 25863 | 0 | 0 | 0 | 0
| GRAND TOTAL AMOUNT : | [5 empty] | 0 | 0 | 0

## Measurement_Liner Works_Total
NAME OF WORK - SECURED LANDFILL
HINDUSTAN ENVIRO LIFE PROTECTION SERVICES LIMITED, VADGAM, KHAMBHAT
BILL OF QUANTITY FOR SECURED LANDFILL - CIVIL WORKS
SL NO | BRIEF DESCRIPTION OF ITEM | UNIT | Nos | L | B | H | Qty
1 | 1.5 mm HDPE Liner
The item includes providing and laying of 1500 microns virgin quality HDPE liner. It shall be applied on the Geosynthetic Clay Liner and anchored below in the soil as shown in the section drawing. It shall be sealed and packed from both ends with the existing layers by employing combiwedge fusion process. The over lapping between two HDPE sheets shall be minimum 100 mm and the machine welding shall produce two sealing lines between one overlap for perfect sealing of the liner. The lining material shall be of highest quality high density polyethylene (HDPE) sheeting, manufactured in using virgin high density polyethylene resin entirely free of Plasticizers or other filler materials with all labours, tools, tackles, machineries and transportation. The material should comply all the physico chemical properties as specified i.e. Tear resistance, Puncture resistance, Tensile strength at yield and break, Carbon black content, density, etc. All the individual sheets shall be tested accordingly. The measurements shall be taken of the covered area only and no overlaps will be considered. Refer Item No. 1 for detailed specifications of Technical Specifications of liner works in the Technical Bid Document. - NON SOR ITEM - MARKET RATE
| Bottom Primary Liner layer | Sq.M. | 1 | 34860 |  | 1 | 34860
| Bottom Secondary Liner layer | Sq.M. | 1 | 34860 |  | 1 | 34860
| On Vertical Wall | Sq.M. | 1 | 792 |  | 10.364 | 8208.288
| Primary Liner on Wall thickness + kerb wall height above road | Sq.M. | 1 | 792 |  | 1.67 | 1322.64
| Secondary Liner on Wall thickness + kerb wall height above road | Sq.M. | 1 | 792 |  | 1.67 | 1322.64
| In Top Road Anchoring Liner | Sq.M. | 1 | 792 |  | 2 | 1584
| Total Qty : | Sq.M. |  |  |  |  | 82157.568
2 | Providing and Laying of 500 gsm Geotextile Liner
The item includes providing and laying of 500 gsm Geotextile liner. Refer Item No. 2 for detailed specifications of Technical Specifications of liner works in the Technical Bid Document. NON SOR ITEM - MARKET RATE
| Bottom Primary Liner layer | Sq.M. | 1 | 34860 |  | 1 | 34860
| Bottom Secondary Liner layer | Sq.M. | 1 | 34860 |  | 1 | 34860
| On Vertical Wall | Sq.M. | 1 | 792 |  | 10.364 | 8208.288
| Primary Liner on Wall thickness + kerb wall height above road | Sq.M. | 1 | 792 |  | 1.67 | 1322.64
| Secondary Liner on Wall thickness + kerb wall height above road | Sq.M. | 1 | 792 |  | 1.67 | 1322.64
| In Top Road Anchoring Liner | Sq.M. | 1 | 792 |  | 2 | 1584
| Total Qty : | Sq.M. |  |  |  |  | 82157.568
3 | Providing and Laying of 150 GSM unprocessed non woven Geotextile Liner
| The item includes providing and laying of 150 gsm unprocessed non woven Geotextile liner laid and wrapped over the 160/225 mm HDPE perforated leachate collection pipe so as to allow leachate to flow to the leachate collection pipe and finally to the leachate collection well. This shall permit high flow of leachate into the leachate collection pipe and shall carry leachate to the leachate well. The liner shall be placed over the leachate collection pipe system as shown in the drawing. Refer Item No. 3 for detailed specifications of Technical Specifications of liner works in the Technical Bid Document. - NON SOR ITEM - MARKET RATE |  |  |  | Perimeter
| For Lateral Pipe ( 160mm Dia ) wrapping | Sq.M. | 1 | 1768 | 0.75 | 1 | 1326
| For Header Pipe ( 225mm Dia ) wrapping | Sq.M. | 1 | 332 | 1.05 | 1 | 348.6
| Total Qty : | Sq.M. |  |  |  |  | 1674.6
4 | Supplying and applying Two coat of HOT BITUMEN VG10 grade conforming to IS:73 @2.0 Kg/sq.m. on Concrete/Brick work surfaces etc.
The item includes Supplying and applying one coat of HOT BITUMEN VG10 grade conforming to IS:73 @1.2 Kg/sq.m. & Supplying and applying Second coat of HOT BITUMEN VG10 grade conforming to IS:73 @0.8 Kg/sq.m. to be applied on the RCC retaining wall surface inside as well as on outside to prevent corrosion of RCC and Steel due to coastal area. This shall prevent any chemical attack on the concrete surface from the chemicals present in the hazardous wastes. The hot bitumen shall be applying over the retaining wall and on outer slopein hot conditions as shown in the drawing. Refer Item No. 4 for detailed specifications of Technical Specifications of liner works in the Technical Bid Document. - NON SOR ITEM - MARKET RATE
| On Raft Inside | Sq.M. | 1 | 802 | 1 | 0.75 | 601.5
| On Top of Raft - Inside | Sq.M. | 1 | 802 | 3.1 | 1 | 2486.2
| On Vertical Wall - Inside + Top of Wall + up to Road | Sq.M. | 1 | 792 | 1 | 14 | 11088
| On Road Kerb Wall & Outer Side Slope | Sq.M. | 1 | 850 | 1 | 13.75 | 11687.5
| Total Qty : | Sq.M. |  |  |  |  | 25863.2

## Measurement_Civil Works_Phase1
NAME OF WORK - SECURED LANDFILL
HINDUSTAN ENVIRO LIFE PROTECTION SERVICES LIMITED, VADGAM, KHAMBHAT
BILL OF QUANTITY FOR SECURED LANDFILL - CIVIL WORKS FOR PHASE - 1 WALL HEIGHT - 5.4 M
SL NO | BRIEF DESCRIPTION OF ITEM | UNIT | Nos | L | B | H | Qty
Earth Work at the base of the phase
1 | Mass Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead.
Soft Soil
| Inside Bottom Area | Cu.M. | 1 | 31860 |  | 0.5 | 15930
| Total Qty : | Cu.M. |  |  |  |  | 15930
2 | Providing and laying 300mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete.
| Inside Bottom Area | Cu.M. | 1 | 32435 |  | 0.3 | 9730.5
| Total Qty : | Cu.M. |  |  |  |  | 9730.5
Construction of Earthen Bund on the Periphery of the phase at the back of RCC retaining wall:
2 | The item includes filling foundation and plinth with murrum or selected soil brought from outside of the site to construct earthen bunds on the periphery of the phase in layers not exceeding 23 cm. in depth and in such a way to maintain the prescribed side slope as shown. The item includes Excavation from borrow pits, transporting upto 25 km lead, filling, leveling, grading, dressing, watering and compaction of the earth from the excavation point to make earthen bunds in the prescribed side slopes.
| Back Side of Landfill RCC Wall | Cu.M. | 1 | 850 | 4.3 | 5 | 18275 | B = 2.6 + 6.0/2 = 4.30
| Outer Footing Below NGL | Cu.M. | 1 | 813 | 5.6 | 0.3 | 1365.84
| Total Qty : | Cu.M. |  |  |  |  | 19640.84
Construction of Retaining Wall in RCC M25 at the EGL of 10.364 m height and supported by RCC counterfortes:
3 | The item includes construction of RCC M25 retaining wall of 300 mm thickness and 10.364 m total height at the existing ground level to increase the capacity of the phase. The wall shall be supported by RCC counterfortes and soil filling shall be done at the back of the wall for further support. The design and details are shown in the drawings.
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 100 mt. lead.
| At Base of Landfill RCC Wall | Cu.M. | 1 | 802 | 10.5 | 1.5 | 12631.5
| Total Qty : | Cu.M. |  |  |  |  | 12631.5
b | Providing and laying 300mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete.
| At Base of Landfill RCC Wall | Cu.M. | 1 | 802 | 9.3 | 0.3 | 2237.58
| Total Qty : | Cu.M. |  |  |  |  | 2237.58
c | Providing and laying 150 mm thk. plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| At Base of Landfill RCC Wall | Cu.M. | 1 | 802 | 9.3 | 0.15 | 1118.79
| Total Qty : | Cu.M. |  |  |  |  | 1118.79
d | Providing and laying controlled cement concrete M-25 on the PCC laid above and curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing in Foundations, footings, base of columns and mass concrete.
| Footing of RCC Wall | Cu.M. | 1 | 802 | 9 | 0.75 | 5413.5
| Total Qty : | Cu.M. |  |  |  |  | 5413.5
e | Wall and counterfortes from top of foundation level up to top height of wall.
| Vertical Wall | Cu.M. | 1 | 794 | 0.3 | 5.4 | 1286.28
| Counter Fortes on the back side of Wall | Cu.M. | 378 | 4.685 | 0.3 | 5.3 | 2815.7787 | L = 3.77 +5.6/2
| Total Qty : | Cu.M. |  |  |  |  | 4102.0587 | 4.685
f | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. |  |  |  | Unit Wt. Kg per Cum
| Footing of RCC Wall | Kg | 1 | 5413.5 | 80 | 1 | 433080
| Verti Wall | Kg | 1 | 1286.28 | 100 | 1 | 128628
| Counter Fall back side Wall | Kg | 1 | 2815.7787 | 100 | 1 | 281577.87
| Total Qty : | Kg |  |  |  |  | 843285.87
g | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete and vertical wall structure.
| For PCC at Base of Footing - Along Length | Sq.M. | 2 | 802 | 1 | 0.15 | 240.6
| For PCC at Base of Footing - Across Length | Sq.M. | 2 | 9 | 1 | 0.15 | 2.7
| For Footing of RCC Wall - Along Length | Sq.M. | 2 | 802 | 1 | 0.9 | 1443.6
| For Footing of RCC Wall - Across Length | Sq.M. | 2 | 9 | 1 | 0.9 | 16.2
| Verti Wall - Along Length | Sq.M. | 1 | 792 | 1 | 5.4 | 4276.8
| Verti Wall - Along Length | Sq.M. | 1 | 688 | 1 | 5.4 | 3715.2
| Verti Wall - Across Length | Sq.M. | 2 | 0.3 | 1 | 5.4 | 3.24
| Counter Forts Along Height & Width | Sq.M. | 756 | 4.69 | 1 | 5.3 | 18791.892
| Counter Forts Across Height & Width | Sq.M. | 378 | 0.3 | 1 | 5.6 | 635.04
| Total Qty : | Sq.M. |  |  |  |  | 29125.272
h | Providing and Laying of flat ribbed PVC Water stopper in the 25 mm wide expansion joint provided in the retaining RCC wall of size 300 mm x 8 mm over the total height of the wall. | Rmt | 15 | 5.4 |  |  | 81
i | Providing and fixing 25 mm thk. HD100 Polymer Expansion joint filler board in the expansion joint of the retaining wall and its counter fortes structure: 25 mm thk. HD100 Polymer based expansion joint filler board is a cross linked, pre moulded high performance joint filler board. It is readily compressible and ensures low load transfer. It is a closed cell with excellent chemical resistance, thermally stable upto 70oC, and very compressible as well as elastic with almost more than 90% recoverable to its original state and rot proof and bacteria resistant. | Sq.m. | 15 | 1 | 5.9 | 5.4 | 477.9
Amended Clay Liner in the Bottom - 2 Layers of 450 mm thickness
4 | The item includes P/L of amended clay liner using the available soil obtained from excavation of the phase as well as from the nearby borrow pits and mixing with good quality sodium bentonite in appropriate proportion with soil to achieve the desired permeability as specified in criteria of CPCB, on the bottom surface of the phase in two layers of 450 mm thickness as shown in the bottom liner section. The contractor shall mix the excavated soil and bentonite to fill the bottom liner in 450 mm thickness and compacted thorughly. See Item No.4 of Item wise specifications.
| Inside Bottom Area - 1st layer | Cu.M. | 1 | 34860 |  | 0.45 | 15687
| Inside Bottom Area - 2nd layer | Cu.M. | 1 | 34860 |  | 0.45 | 15687
| Total Qty : | Cu.M. |  |  |  |  | 31374
Drainage Layer at the Bottom of phase - 2 layers of 300 mm thickness
5 | The item includes providing and laying of 300 mm drainage layer - primary and secondary layers comprising of 100mm thick 12-25 mm round gravels/Coarse Aggregate + 100 mm thick 3-12mm round gravels/Coarse Aggregate (Grit) + 100 mm thk. Coarse sand as shown in drawing. The item includes providing, laying, leveling, compaction etc. complete. See Item No.5 of Item wise specifications.
a | 100 mm thk. 12 -25 mm round gravels/coarse aggregate
| Inside Bottom Area - 1st layer | Cu.M. | 1 | 34860 |  | 0.1 | 3486
| Inside Bottom Area - 2nd layer | Cu.M. | 1 | 34860 |  | 0.1 | 3486
| Total Qty : | Cu.M. |  |  |  |  | 6972
b | 100 mm thk. 3 -12 mm round gravels/coarse aggregate
| Inside Bottom Area - 1st layer | Cu.M. | 1 | 34860 |  | 0.1 | 3486
| Inside Bottom Area - 2nd layer | Cu.M. | 1 | 34860 |  | 0.1 | 3486
| Total Qty : | Cu.M. |  |  |  |  | 6972
c | 100 mm thk. Coarse sand
| Inside Bottom Area - 1st layer | Cu.M. | 1 | 34860 |  | 0.1 | 3486
| Inside Bottom Area - 2nd layer | Cu.M. | 1 | 34860 |  | 0.1 | 3486
| Total Qty : | Cu.M. |  |  |  |  | 6972
Top Service Road of the Phase
6 | Providing and laying of 3.75 M Clear Wide CC road on the top periphery of the phase. The item includes excavation, 230 mm thk. Rubble Soling, 100 mm thk. PCC (1:4:8) and 100 mm thk. RCC M20 construction on the road. Total road area 3236 Sq.m.:
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead.
| For Top Road surface dressing | Cu.M. | 1 | 0 | 0 | 0 | 0
| Total Qty : | Cu.M. |  |  |  |  | 0
b | Providing and laying 230mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete.
| For Top Road rubble soling | Cu.M. | 1 | 0 | 0 | 0 | 0
| Total Qty : | Cu.M. |  |  |  |  | 0
c | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| For Top Road PCC | Cu.M. | 1 | 0 | 0 | 0 | 0
| Total Qty : | Cu.M. |  |  |  |  | 0
d | Providing and laying controlled cement concrete M-20 on the PCC laid above and curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing in Foundations, footings, base of columns and mass concrete.
| For Top Road RCC | Cu.M. | 1 | 0 | 0 | 0 | 0
| Total Qty : | Cu.M. |  |  |  |  | 0
e | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. |  |  |  | Unit Wt. Kg per Cum
| For Top Road RCC | Kg | 1 | 0 | 0 | 0 | 0
| Total Qty : | Kg |  |  |  |  | 0
f | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete.
| For PCC - Along Length | Sq.M. | 2 | 0 | 0 | 0 | 0
| For PCC - Across Length | Sq.M. | 2 | 0 | 0 | 0 | 0
| For RCC - Along Length | Sq.M. | 2 | 0 | 0 | 0 | 0
| For RCC - Across Length | Sq.M. | 2 | 0 | 0 | 0 | 0
| Total Qty : | Sq.M. |  |  |  |  | 0
Kerb Wall on the Outer Edge of the Top Service Road - 300 mm high and 250 mm thk. - 830 m long
7 | Construction of Kerb Wall on the outer edge of the 4.0 M Wide (3.75 M clear wide) Top service road on the top periphery of the phase. The item includes 250 mm thk. and 300 mm high RCC M20 construction on the road. See Item No.7 of Item wise specifications.
a | Providing and laying controlled cement concrete M-20 on the PCC laid above and curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing in Foundations, footings, base of columns and mass concrete.
| For Top Road RCC | Cu.M. | 1 | 0 | 0 | 0 | 0
| Total Qty : | Cu.M. |  |  |  |  | 0
b | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. |  |  |  | Unit Wt. Kg per Cum
| For Top Road RCC | Kg | 1 | 0 | 80 | 0 | 0
| Total Qty : | Kg |  |  |  |  | 0
c | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete.
| For RCC - Along Length | Sq.M. | 2 | 0 | 0 | 0 | 0
| For RCC - Across Length | Sq.M. | 2 | 0 | 0 | 0 | 0
| Total Qty : | Sq.M. |  |  |  |  | 0
Outer Side Slope Construction
8 | Following works are to be carried out on the outer side slope of total length 12.90 Avg. m. The item includes protection of Outer side slope by P/L of 230 mm thk. Rubble Soling, 100 mm thk. PCC (1:4:8) and 100 mm thk. RCC M20 on the outer side slope. Total Area of outer side slope is 10965 Sq.m.
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead.
| For Outer Side Slope surface dressing | Cu.M. | 1 | 0 | 0 | 0 | 0
| Total Qty : | Cu.M. |  |  |  |  | 0
b | Providing and laying 230mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete.
| For Outer Side Slope Rubble Soling | Cu.M. | 1 | 0 | 0 | 0 | 0
| Total Qty : | Cu.M. |  |  |  |  | 0
c | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| For Outer Side Slope PCC | Cu.M. | 1 | 0 | 0 | 0 | 0
| Total Qty : | Cu.M. |  |  |  |  | 0
d | Providing and laying controlled cement concrete M-20 on the PCC laid above and curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing in Foundations, footings, base of columns and mass concrete.
| For Outer Side Slope RCC | Cu.M. | 1 | 0 | 0 | 0 | 0
| Total Qty : | Cu.M. |  |  |  |  | 0
e | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. |  |  |  | Unit Wt. Kg per Cum
| For Outer Side Slope RCC | Kg | 1 | 0 | 45 | 0 | 0
| Total Qty : | Kg |  |  |  |  | 0
f | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete.
| PCC - Along Length | Sq.M. | 0 | 0 | 0 | 0 | 0
| RCC - Along Length | Sq.M. | 0 | 0 | 0 | 0 | 0
| Total Qty : | Sq.M. |  |  |  |  | 0
Storm Water Drain - 1020 m long, 0.50 m wide and 0.40 m deep [ 912 m around Landfill adjacent to toewall & 108 m other area without toewall]
9 | The item includes construction of Storm Water Drain in RCC on the bottom outer edge of the outer side slope on the G/L. The item includes excavation, Rubble Soling, PCC and RCC M20.
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead.
| For Drain around Landfill Cell | Cu.M. | 1 | 912 | 0.515 | 0.855 | 401.5764
| For Drain other portion | Cu.M. | 1 | 108 | 1.05 | 0.86 | 97.524
| Total Qty : | Cu.M. |  |  |  |  | 499.1004
b | Providing and laying 230mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete.
| For Drain around Landfill Cell | Cu.M. | 1 | 912 | 0.925 | 0.23 | 194.028
| For Drain other portion | Cu.M. | 1 | 108 | 1.05 | 0.23 | 26.082
| Total Qty : | Cu.M. |  |  |  |  | 220.11
c | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| For Drain around Landfill Cell | Cu.M. | 1 | 912 | 0.775 | 0.1 | 70.68
| For Drain other portion | Cu.M. | 1 | 108 | 1.05 | 0.1 | 11.34
| Total Qty : | Cu.M. |  |  |  |  | 82.02
d | Providing and laying controlled cement concrete M-20 on the PCC laid above and curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing in Foundations, footings, base of columns and mass concrete.
| For Drain around Landfill Cell - Bottom | Cu.M. | 1 | 912 | 0.625 | 0.125 | 71.25
| For Drain of other portion - Bottom | Cu.M. | 1 | 108 | 0.75 | 0.125 | 10.125
| For Drain around Landfill Cell - Inner Wall | Cu.M. | 1 | 912 | 0.23 | 0.4 | 83.904
| For Drain of other portion - Inner Wall | Cu.M. | 1 | 108 | 0.23 | 0.4 | 9.936
| For All Drain Length - Outer Wall | Cu.M. | 1 | 1020 | 0.125 | 0.4 | 51
| Total Qty : | Cu.M. |  |  |  |  | 226.215
e | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. |  |  |  | Unit Wt. Kg per Cum
| For All Drain Length | Kg | 1 | 226.215 | 85 | 1 | 19228.275
| Total Qty : | Kg |  |  |  |  | 19228.275
f | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete.
| For All Drain Length - PCC | Sq.M. | 2 | 1020 | 1 | 0.1 | 204
| For All Drain Length - Inner Face | Sq.M. | 2 | 1020 | 1 | 0.4 | 816
| For All Drain Length - Outer Face | Sq.M. | 2 | 1020 | 1 | 0.525 | 1071
| Total Qty : | Sq.M. |  |  |  |  | 2091
Toe Wall in Brick Masonary on outer side slope outer edge - 912 m length in landfill periphery
10 | The item includes construction of Toe Wall in Brick Masonary on the bottom outer edge of the outer side slope on the G/L. The item includes excavation, rubble soling, PCC, B/M and Plaster.
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead.
| At the End of Outer Slope | Cu.M. | 1 | 912 | 1.05 | 1.655 | 1584.828
| Total Qty : | Cu.M. |  |  |  |  | 1584.828
b | Providing and laying 230mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete.
| At the Base of Toe Wall | Cu.M. | 1 | 912 | 1.05 | 0.23 | 220.248
| Total Qty : | Cu.M. |  |  |  |  | 220.248
c | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| At the Fdn of Toe Wall - PCC | Cu.M. | 1 | 912 | 0.75 | 0.1 | 68.4
| Total Qty : | Cu.M. |  |  |  |  | 68.4
d | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete.
| For Toe Wall - PCC - Along Length | Sq.M. | 2 | 912 | 1 | 0.1 | 182.4
| For Toe Wall - PCC - Across Length | Sq.M. | 2 | 1 | 0.75 | 0.1 | 0.15
| Total Qty : | Sq.M. |  |  |  |  | 182.55
e | Providing and laying the brick masonary of well burnt bricks of approved quality and manufacturer in cement mortar 1:6 prop. using screened coarse sand upto 3Meter Height including scaffolding.
| For Toe Wall - 450mm width | Cu.M. | 1 | 912 | 0.45 | 0.23 | 94.392
| For Toe Wall - 350mm width | Cu.M. | 1 | 912 | 0.35 | 0.24 | 76.608
| For Toe Wall - 230mm width | Cu.M. | 1 | 912 | 0.23 | 0.33 | 69.2208
| Total Qty : | Cu.M. |  |  |  |  | 240.2208
f | Providing and applying 20 mm thick smooth plaster in cement mortar 1:4 prop., using screened coarse sand of approved quality on brick walls and RCC work as required incl. racking of joints of masonary and roughening of concrete surface (i.e. hacking) to receive plaster, with the use of approved water proofing admixture, with scaffolding to any height, finishing smooth with cement slurry mixing, applying, watering, curing with all labour and materials.
| For Toe Wall - Both Sides - 230 mm width | Sq.M. | 2 | 912 | 1 | 0.33 | 601.92
| For Toe Wall - Both Sides - 350 mm width | Sq.M. | 2 | 912 | 1 | 0.24 | 437.76
| For Toe Wall - Both Sides - 450 mm width | Sq.M. | 2 | 912 | 1 | 0.23 | 419.52
| For RCC Drain - Outer Side | Sq.M. | 2 | 912 | 1 | 0.525 | 957.6
| For RCC Drain - Inside | Sq.M. | 2 | 912 | 1 | 0.4 | 729.6
| For RCC Drain - Top & Bottom of Drain | Sq.M. | 1 | 912 | 1 | 0.855 | 779.76
| Total Qty : | Sq.M. |  |  |  |  | 3926.16
Leachate Well in RCC M25 - 4 Nos. - 6.0 m x 2.0 m x 2.665 m (H)
11 | The leachate wells have to be constructed in RCC M250 grade concrete of size 6.0 m x 2.0 m x 2.665 m (H) with 200 mm thickness wall as shown in the drawing. The well shall be kept partly covered from the top.
a | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead.
| Leachate Tank Fdn - 4 Nos | Cu.M. | 4 | 7.9 | 3.9 | 2.67 | 329.0508
| Total Qty : | Cu.M. |  |  |  |  | 329.0508
b | P/L of Rubble Soling in the Raft of the Tank
| Leachate Tank Fdn Rubble Soling - 4 Nos | Cu.M. | 4 | 7.9 | 3.9 | 0.3 | 36.972
| Total Qty : | Cu.M. |  |  |  |  | 36.972
c | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| Leachate Tank Fdn PCC - 4 Nos | Cu.M. | 4 | 7.3 | 3.3 | 0.15 | 14.454
| Total Qty : | Cu.M. |  |  |  |  | 14.454
d | Providing and laying controlled cement concrete M-25 in the raft and walls and slab of the wells and includes curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing.
| Leachate Tank RCC Raft - 4 Nos | Cu.M. | 4 | 7 | 3 | 0.3 | 25.2
| Leachate Tank RCC Long Wall - 4 Nos | Cu.M. | 8 | 6 | 0.2 | 2.665 | 25.584
| Leachate Tank RCC Short Wall - 4 Nos | Cu.M. | 8 | 2 | 0.2 | 2.665 | 8.528
| Leachate Tank RCC Top Slab - 4 Nos | Cu.M. | 4 | 6 | 2 | 0.1 | 4.8
| Deduct : Slab Open Space - 4 Nos | Cu.M. | 4 | 2 | 2 | 0.1 | -1.6
| Total Qty : | Cu.M. |  |  |  |  | 62.512
e | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. |  |  |  | Unit Wt. Kg per Cum
| For All Drain Length | Kg | 1 | 62.512 | 90 | 1 | 5626.08
| Total Qty : | Kg |  |  |  |  | 5626.08
f | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete.
| For PCC - 4 Nos | Sq.M. | 8 | 7.3 | 1 | 0.15 | 8.76
| For PCC - 4 Nos | Sq.M. | 8 | 3.3 | 1 | 0.15 | 3.96
| For RCC Raft - 4 Nos | Sq.M. | 8 | 7 | 1 | 0.3 | 16.8
| For RCC Raft - 4 Nos | Sq.M. | 8 | 3 | 1 | 0.3 | 7.2
| For RCC Long Wall - Out Side - 4 Nos | Sq.M. | 8 | 6.4 | 1 | 2.665 | 136.448
| For RCC Long Wall - In Side - 4 Nos | Sq.M. | 8 | 6 | 1 | 2.565 | 123.12
| For RCC Short Wall - Out Side - 4 Nos | Sq.M. | 8 | 2.4 | 1 | 2.665 | 51.168
| For RCC Short Wall - In Side - 4 Nos | Sq.M. | 8 | 2 | 1 | 2.565 | 41.04
| For RCC Slab Bottom - 4 Nos | Sq.M. | 8 | 6 | 2 | 1 | 96
| Deduct : Open Space in RCC Slab Bottom - 4 Nos | Sq.M. | 4 | 2 | 2 | 1 | -16
| Total Qty : | Sq.M. |  |  |  |  | 468.496
Leachate Collection system - Leachate pipes - 160 mm outer dia lateral pipes - 1768 m Length and 225 mm oter dia main header pipes - 332 m Length laid in RCC leachate Collection trench placed at the bottom of the phase in the Primary Leachate Collection layer
12 | The item includes providing and laying of 160 mm outer diameter size HDPE pipes of 10 Kg/cm2 pressure grade and ISI make as per IS – 4984 with material grade PE – 80 and material density of 946.40 Kg/cm2 and having holes of 10 mm @ center to center 200 mm distance in the upper half section of the pipes, through out the length of the pipes as shown in the diagram attached. The pipes are to be laid horizontally in the primary drainage layer at the bottom of the phase as shown in the layout plan of the landfill and are connected with the RCC leachate wells. The pipes connecting the leachate well are to be laid in such a way so as to make a slope of 1.0 % available to allow leachate to flow easily in to the Leachate well. The pipes are to be laid in a RCC leachate collection trench. The Leachate wells are to be connected to a 225 mm outer diameter main header. The leachate wells shall have a leachate lifting system with sludge pumps provided at the G/L and delivery pipe brought to the G/L at the approach ramps and provided with valves for discharging leachate to the leachate tank. See Item No. 12 of Item wise specifications.
a | Providing and Laying of 160 mm diameter HDPE pipes of 10 Kg/CM2 grade and ISI make with perforations for leachate collection.
| Lateral Pipe | R.mt. | 1 | 1768 | 1 | 1 | 1768
| Total Qty : | R.mt. |  |  |  |  | 1768
b | Providing and Laying of 225 mm diameter HDPE pipes of 10 Kg/CM2 grade and ISI make without perforations for leachate collection - whole main header pipe.
| Header Pipe | R.mt. | 1 | 332 | 1 | 1 | 332
| Total Qty : | R.mt. |  |  |  |  | 332
c | Providing and Laying of RCC Leachate Collection Trench to fix pipes at specified locations – 1768 m for 160mm Perforated HDPE pipes and 332 m for 225 mm main Header Pipe - Total 2100 m length:
c.1 | Excavation executed with mechanised efforts/machineries for foundation upto 1.5 m depth from EGL including sorting out stacking of useful material & disposing off excavated stuff upto 200 mt. lead.
| For Header & Lateral Pipe | Cu.M. | 1 | 2100 | 1.075 | 0.36 | 812.7
| Total Qty : | Cu.M. |  |  |  |  | 812.7
c.2 | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| For Header & Lateral Pipe | Cu.M. | 1 | 2100 | 1.8 | 0.1 | 378
| Total Qty : | Cu.M. |  |  |  |  | 378
c.3 | Providing and laying controlled cement concrete M-20 in the raft and walls of the wells and includes curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing.
| For Header & Lateral Pipe | Cu.M. | 1 | 2100 | 1.4 | 0.1 | 294
| Total Qty : | Cu.M. |  |  |  |  | 294
c.4 | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. |  |  |  | Unit Wt. Kg per Cum
| For Header & Lateral Pipe - RCC Bottom | Kg | 1 | 294 | 60 | 1 | 17640
| Total Qty : | Kg |  |  |  |  | 17640
d | Providing and Laying of Sludge pumps with complete electrical system including high efficiency motor, operating at a discharge head of 30 m minimum and delivering the leachate at the rate of 50 Cum/Hr. - NON SOR ITEM
| Sludge Pump - 4 Nos Tank | No. | 4 | 1 | 1 | 1 | 4
| Total Qty : | No. |  |  |  |  | 4
Construction of Outer Side Entrance Ramp up to Top Road for 5.4 m height wall construction in Phase -1
13 | The item includes construction of Outer Entrance Ramp for Truck movement into and out of the phase. Total Ramp Length is 76 Rmt and 7.0 m wide, with top area of 548 Sq.m. And Side Slope area of 538 Sq.m.to be constructed by filling of soil and followed by rubble stone filling and kerb wall on both sides in brick masonary.
a | The item includes filling foundation and plinth with murrum or selected soil brought from outside of the site to construct outer ramp for truck into & out to in layers not exceeding 23 cm. in depth and in such a way to maintain the prescribed side slope as shown. The item includes Excavation from borrow pits, transporting upto 25 km lead, filling, leveling, grading, dressing, watering and compaction of the earth from the excavation point to make outer ramp in the prescribed side slopes.
| Soil in Rectangular portion of 7 m width | Cu.M. | 1 | 76 | 7 | 2.529 | 1345.428
| Soil in Triangular portion of varying length | Cu.M. | 1 | 76 | 5.815 | 2.53 | 1118.1082
| Total Qty : | Cu.M. |  |  |  |  | 2463.5362
b | Providing and laying 300mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete.
| On top portion of 7 m width | Cu.M. | 1 | 76 | 7 | 0.3 | 159.6
| On side Slope portion | Cu.M. | 1 | 76 | 7.08 | 0.3 | 161.424
| Total Qty : | Cu.M. |  |  |  |  | 321.024
c | Providing and laying plain cement concrete (1:4:8) at the outer edges of ramp and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| At the outer edge of the ramp | Cu.M. | 1 | 76 | 0.445 | 0.1 | 3.382
| Total Qty : | Cu.M. |  |  |  |  | 3.382
d | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete.
| For PCC - Along Length | Sq.M. | 25 | 9.75 | 1 | 0.1 | 24.375
| For PCC - Across Length | Sq.M. | 2 | 1 | 0.345 | 0.1 | 0.069
| Total Qty : | Sq.M. |  |  |  |  | 24.444
e | Providing and laying the brick masonary of well burnt bricks of approved quality and manufacturer in cement mortar 1:6 prop. using screened coarse sand in the kerb wall of size 345 mm (B) x 600 mm (H)
| For Kerb Wall - 345 mm width | Cu.M. | 2 | 76 | 0.345 | 0.6 | 31.464
| Total Qty : | Cu.M. |  |  |  |  | 31.464
Construction of Outer Side Entrance Ramp up to Top Road for 8.70 m height wall construction in Phase -2 + Entrance area development
14 | The item includes construction of Outer Entrance Ramp for Truck movement into and out of the phase. Total Ramp Length is 112.50 Rmt and 7.0 m wide, with top area of 785.50 Sq.m. And Side Slope area of 1335 Sq.m.to be constructed by filling of soil and followed by rubble stone filling, followed by PCC and RCC and kerb wall on both sides in RCC. It also includes construction of entrance area development in RCC. Additional Entrance Area to be developed is 1045 Sq.m. as shown in the layout drawing. See Item No. 14 of Item wise specifications.
a | The item includes filling foundation and plinth with murrum or selected soil brought from outside of the site to construct outer ramp for truck into & out to in layers not exceeding 23 cm. in depth and in such a way to maintain the prescribed side slope as shown. The item includes Excavation from borrow pits, transporting upto 25 km lead, filling, leveling, grading, dressing, watering and compaction of the earth from the excavation point to make outer ramp in the prescribed side slopes.
| Soil in Rectangular portion of 7 m width | Cu.M. | 0 | 0 | 0 | 0 | 0
| Soil in Triangular portion of varying length | Cu.M. | 0 | 0 | 0 | 0 | 0
| Soil in Entrance Area | Cu.M. | 0 | 0 | 0 | 0 | 0
| Total Qty : | Cu.M. |  |  |  |  | 0
b | Providing and laying 230mm thk.rubble stone filling with 33% murrum in specified thickness with watering, compaction etc. complete.
| On top portion of 7 m width | Cu.M. | 0 | 0 | 0 | 0 | 0
| On side Slope portion | Cu.M. | 0 | 0 | 0 | 0 | 0
| On Entrance Area | Cu.M. | 0 | 0 | 0 | 0 | 0
| Total Qty : | Cu.M. |  |  |  |  | 0
c | Providing and laying plain cement concrete (1:4:8) at the excavated areas and it includes machine mixing, watering, laying, spreading, leveling, consolidating, curing etc. complete with all labour and materials without form work and reinforcement.
| On top portion of 7 m width | Cu.M. | 0 | 0 | 0 | 0 | 0
| On side Slope portion | Cu.M. | 0 | 0 | 0 | 0 | 0
| On Entrance Area | Cu.M. | 0 | 0 | 0 | 0 | 0
| Total Qty : | Cu.M. |  |  |  |  | 0
d | Providing and laying controlled cement concrete M-20 over the PCC area including all areas of the ramp and includes curing complete, exculding form work and reinforcement for reinforced concrete work as shown in the drawing.
| On top portion of 7 m width | Cu.M. | 0 | 0 | 0 | 0 | 0
| On side Slope portion | Cu.M. | 0 | 0 | 0 | 0 | 0
| In kerb wall on outer edge on both sides | Cu.M. | 0 | 0 | 0 | 0 | 0
| On Entrance Area | Cu.M. | 0 | 0 | 0 | 0 | 0
| Total Qty : | Cu.M. |  |  |  |  | 0
e | Supplying, cutting, bending, binding and hooking and binding with wire for RCC work in raft, wall and counterfortes Fe500 Grade ISI Brand TMT bars including all cost and placing in position complete. |  |  |  | Unit Wt. Kg per Cum
| For Ramp - RCC | Kg | 0 | 0 | 70 | 0 | 0
| Total Qty : | Kg |  |  |  |  | 0
f | Providing and Laying of Form work with sheeting of steel sheets so as to give a fair finish for concrete structure at the base as mentioned above as shown in the drawing and including centering, shuttering and propping etc. and removal of the same for in situ reinforced concrete and plain concrete work in Foundations,footings, bases of columns and mass concrete.
On top portion of ramp
| For PCC - Along Length | Sq.M. | 0 | 0 | 0 | 0 | 0
| For PCC - Across Length | Sq.M. | 0 | 0 | 0 | 0 | 0
| For RCC - Along Length | Sq.M. | 0 | 0 | 0 | 0 | 0
| For RCC - Across Length | Sq.M. | 0 | 0 | 0 | 0 | 0
| For Kerb wall Along length | Sq.M. | 0 | 0 | 0 | 0 | 0
On side slope portion of ramp
| For PCC | Sq.M. | 0 | 0 | 0 | 0 | 0
| For RCC | Sq.M. | 0 | 0 | 0 | 0 | 0
| On Entrance Area for PCC | Sq.M. | 0 | 0 | 0 | 0 | 0
| On Entrance Area for RCC | Sq.M. | 0 | 0 | 0 | 0 | 0
| Total Qty : | Sq.M. |  |  |  |  | 0

## Measurement_Liner Works_Phase1
NAME OF WORK - SECURED LANDFILL
HINDUSTAN ENVIRO LIFE PROTECTION SERVICES LIMITED, VADGAM, KHAMBHAT
BILL OF QUANTITY FOR SECURED LANDFILL - CIVIL WORKS
SL NO | BRIEF DESCRIPTION OF ITEM | UNIT | Nos | L | B | H | Qty
1 | 1.5 mm HDPE Liner
The item includes providing and laying of 1500 microns virgin quality HDPE liner. It shall be applied on the Geosynthetic Clay Liner and anchored below in the soil as shown in the section drawing. It shall be sealed and packed from both ends with the existing layers by employing combiwedge fusion process. The over lapping between two HDPE sheets shall be minimum 100 mm and the machine welding shall produce 2 seams. The lining material shall be of highest quality high density polyethylene (HDPE) sheeting, manufactured in using virgin high density polyethylene resin entirely free of Plasticizers or other filler materials with all labours, tools, tackles, machineries and transportation. The material shall not contain more than 3% of carbon black, antioxidants and thermal stabilizers. It should comply all the physico chemical properties as specified i.e. Tear resistance, Puncture resistance, Tensile strength at yield and break, Carbon black content, density, etc. All the individual sheets shall be tested accordingly. The measurements shall be taken of the covered area only and no overlaps will be considered. Refer Item No. 1 for detailed specifications of Technical Specifications of liner works in the Technical Bid Document. - NON SOR ITEM - MARKET RATE
| Bottom Primary Liner layer | Sq.M. | 1 | 34860 |  | 1 | 34860
| Bottom Secondary Liner layer | Sq.M. | 1 | 34860 |  | 1 | 34860
| On Vertical Wall | Sq.M. | 1 | 792 |  | 5.4 | 4276.8
| Primary Liner on Wall thickness | Sq.M. | 1 | 792 |  | 0.3 | 237.6
| Secondary Liner on Wall thickness | Sq.M. | 1 | 792 |  | 0.3 | 237.6
| In Anchoring Liner | Sq.M. | 1 | 792 |  | 2 | 1584
| Total Qty : | Sq.M. |  |  |  |  | 76056
2 | Providing and Laying of 500 gsm Geotextile Liner
The item includes providing and laying of 500 gsm Geotextile liner. Refer Item No. 2 for detailed specifications of Technical Specifications of liner works in the Technical Bid Document. NON SOR ITEM - MARKET RATE
| Bottom Primary Liner layer | Sq.M. | 1 | 34860 |  | 1 | 34860
| Bottom Secondary Liner layer | Sq.M. | 1 | 34860 |  | 1 | 34860
| On Vertical Wall | Sq.M. | 1 | 792 |  | 5.4 | 4276.8
| Primary Liner on Wall thickness | Sq.M. | 1 | 792 |  | 0.3 | 237.6
| Secondary Liner on Wall thickness | Sq.M. | 1 | 792 |  | 0.3 | 237.6
| In Anchoring Liner | Sq.M. | 1 | 792 |  | 2 | 1584
| Total Qty : | Sq.M. |  |  |  |  | 76056
3 | Providing and Laying of 150 GSM unprocessed non woven Geotextile Liner
| The item includes providing and laying of 150 gsm unprocessed non woven Geotextile liner laid and wrapped over the 160/225 mm HDPE perforated leachate collection pipe so as to allow leachate to flow to the leachate collection pipe and finally to the leachate collection well. This shall permit high flow of leachate into the leachate collection pipe and shall carry leachate to the leachate well. The liner shall be placed over the leachate collection pipe system as shown in the drawing. Refer Item No. 3 for detailed specifications of Technical Specifications of liner works in the Technical Bid Document. - NON SOR ITEM - MARKET RATE |  |  |  | Perimeter
| For Lateral Pipe ( 160mm Dia ) wrapping | Sq.M. | 1 | 1768 | 0.75 | 1 | 1326
| For Header Pipe ( 225mm Dia ) wrapping | Sq.M. | 1 | 332 | 1.05 | 1 | 348.6
| Total Qty : | Sq.M. |  |  |  |  | 1674.6
4 | Supplying and applying Two coat of HOT BITUMEN VG10 grade conforming to IS:73 @2.0 Kg/sq.m. on Concrete/Brick work surfaces etc.
The item includes Supplying and applying one coat of HOT BITUMEN VG10 grade conforming to IS:73 @1.2 Kg/sq.m. & Supplying and applying Second coat of HOT BITUMEN VG10 grade conforming to IS:73 @0.8 Kg/sq.m. to be applied on the RCC retaining wall surface inside as well as on outside to prevent corrosion of RCC and Steel due to coastal area. This shall prevent any chemical attack on the concrete surface from the chemicals present in the hazardous wastes. The hot bitumen shall be applying over the retaining wall and on outer slopein hot conditions as shown in the drawing. Refer Item No. 4 for detailed specifications of Technical Specifications of liner works in the Technical Bid Document. - NON SOR ITEM - MARKET RATE
| On Raft Inside | Sq.M. | 1 | 802 | 1 | 0.75 | 601.5
| On Top of Raft - Inside | Sq.M. | 1 | 802 | 3.1 | 1 | 2486.2
| On Vertical Wall - Inside + Top of Wall + On outer side of wall | Sq.M. | 1 | 792 | 1 | 5.8 | 4593.6
| On Road Kerb Wall & Outer Side Slope | Sq.M. | 1 | 0 | 0 | 0 | 0
| Total Qty : | Sq.M. |  |  |  |  | 7681.3